## Exemplar
ROAM Analysis
Issue | Description | Actions/Mitigation Strategy | ROAM designation
Issue 1: LLM response inaccuracies (hallunications) | The LLM may generate responses that are inaccurate,outdated, or not aligned with official council guidance, which could reduce citizen trust and create compliance risks. | Retrieval-Augmented Generation (RAG) is implemented to ground responses in verified council FAQs and service documents. Prompts are constraned to retrieved context only, and fallback guidance redirects users to official council portals when confidence is low. | Mitigated
Issue 2: Sclability under peak demand | Sudden spikes in citizen queries (e.g., council tax deadlines or bin collection changes) may degrade response times or system availability. | A microservices architecture with containerisation is adopted to allow independent scaling of high demand services. Cloud auto-scaliing and monitoring tools are planned to dynamically adjust resources during peak usage. | Owned
Issue 3: Integration with legacy council systems | Integrating the chatbot with existing council CRM,ticketing, or service portals may be technically complex due to legacy constraints and inconsistent APIs. | An API-first design is adopted to decouple the chatbot from backend systems. Where direct integration is not feasible, the chatbot provides guided redirection to official portals instead of real-time data exchange. | Accepted
Issue 4: Data privacy and GDPR compliance | Handling citizen queries may involve sensitive personal data, creating legal and ethical risks if data is stored or processed incorrectly. | The system is designed to minimise data retention, avoid storing personally identifiable information, and rely on secure, cloud-native security controls. Compliance-by-design principles and secure API gateways are used. | Owned
Issue 5: Maintainability of a multi-domain systems | As the chatbot expands across multiple council services, maintaining and updatig knowledge sources and logic may become complex. | Seperation of concerns is enforced through modular microservices and independent knowledge bases per service domain. CI/CD pipelines support controlled updates with minimal downtime. | Mitigated
Issue 6: Vendor lock-in (cloud and LLM providers) | Heavy reliance on a single cloud provider or LLM API may limit future flexibility and increase long-term costs. | The architecture is designed to be vendor-agnostic where possible, using containerisation and API-based LLM access. Alternative cloud platforms and LLM providers can be substituted with minimal architectural change. | Accepted
Issue 7: Accessibility and usability for diverse users | Poor interfae desin may disadvantage vulnerable or digitally excluded citizens. | The frontend is designed to comply with WCAG 2.1 AA accessibility standards, with clear language, simple interaction flows, and escalation paths to human support where needed. | Owned
Issue 8: Measuring conversational quality | Evaluating chatbot performance beyond technical metrics (e.g., usefulness and satisfaction) is inherently difficult. | Evaluation criteria included response time, scalability,ease of updates, and qualitative assessment of response relevance during PoC testing. Continuous improvement is planned post-deployment. | Accepted