## Backlog Simple Epics
Epic | User Story Title | Story | Value (Citizen) | Acceptance Criteria | Complexity | Time | Sprint
Sprint Initiation | Team setup & communication | As a project team, we want to clearly define roles and communication channels for using the chatbot project tools, so that collaboration is effective and everyone understands their responsibilities. | Medium – Establishing clear roles and communication channels supports effective collaboration, helping the team deliver the chatbot project efficiently. | 1) Roles assigned 2) Communication tools agreed | Low | Short | Sprint 0
Sprint Initiation | Group contract | As a project team, we want to create a group contract that outlines expectations and ways of working on the chatbot project, so that conflicts are avoided and accountability is clear. | Low – Defining team expectations helps prevent misunderstandings and supports smoother collaboration throughout the chatbot project. | 1) Contract documented 2) Signed by all members | Low | Short | Sprint 0
Sprint Initiation | Risk assessment | As a project team, we want to carry out a risk assessment for the chatbot project, so that technical, ethical, and delivery risks are identified and mitigated early. | Medium – Identifying and mitigating risks early helps reduce potential delays, technical issues, and ethical problems during chatbot development. | 1) Risks identified 2) Mitigation strategies defined | Medium | Medium | Sprint 0
Research & Planning | Dataset audit | As a project team, we want to audit available council and open datasets for the chatbot, so that we understand what data can be safely and effectively used. | Medium – Reviewing available datasets ensures the chatbot uses appropriate, reliable, and legally compliant data sources. | 1) Data sources listed 2) Data suitability assessed | Medium | Medium | Sprint 1
Research & Planning | Use case analysis | As a project team, we want to analyse citizen chatbot use cases, so that the chatbot functionality aligns with real user needs and council requirements. | Medium – Analysing citizen use cases ensures the chatbot addresses real user needs and aligns with council service requirements. | 1) Use cases documented 2) Prioritisation completed | Medium | Medium | Sprint 1
Core Council Services | Council Tax information | As a resident, I want to ask the chatbot questions about council tax payments and account details, so that I can understand when my payments are due and how to update my details after moving. | High – This feature allows residents to access clear council tax information, reducing confusion and the need to contact council support services. | 1) Council tax guidance provided 2) Links to council portal | Medium | Medium | Sprint 2
Core Council Services | Bin collection information | As a resident, I want to ask the chatbot about my bin and recycling collection schedule, so that I know which bin to put out and when. | High – This feature helps residents understand bin and recycling schedules, reducing missed collections and improving waste management efficiency. | 1) Bin schedules explained 2) Correct service links | Low | Short | Sprint 2
Core Council Services | Missed bin reporting | As a resident, I want to use the chatbot to report a missed bin collection, so that the issue can be logged and resolved without needing to contact the council directly. | High – Enabling residents to report missed bins through the chatbot improves service responsiveness and reduces pressure on contact centres. | 1) Reporting steps explained 2) Online form linked | Low | Short | Sprint 2
Core Council Services | School admissions guidance | As a parent or carer, I want to ask the chatbot about the school admissions process, so that I understand how to apply for a primary school place and meet key deadlines. | High – This feature supports parents and carers by simplifying the school admissions process and reducing uncertainty around applications. | 1) Admissions process explained 2) Deadlines provided | Medium | Medium | Sprint 2
Core Council Services | Benefits & support guidance | As a resident, I want to ask the chatbot whether I may be eligible for housing benefit or other support, so that I can understand what financial help may be available to me. | High – Providing benefits guidance helps residents understand potential financial support, improving access to essential services. | 1) Eligibility explained at a general level 2) Links to eligibility checker/application provided 3) Signposts to additional support services | Medium | Medium | Sprint 2
Core Council Services | Planning application status guidance | As a resident, I want to ask the chatbot how to check the status of a planning application, so that I can stay informed about local developments in my area. | Medium – This feature allows residents to stay informed about local developments, improving transparency and engagement with planning services. | 1) Explains how to find planning applications 2) Links to planning portal/search page 3) Explains common status terms (e.g., submitted, validated, decided) | Medium | Medium | Sprint 2
Community Services | Blue Badge services | As a resident, I want to ask the chatbot how to apply for a Blue Badge, so that I can understand the eligibility requirements and application process for disabled parking. | Medium – This feature helps eligible residents understand and access mobility support, improving inclusivity and independence. | 1) Eligibility explained 2) Application steps linked | Low | Short | Sprint 3
Community Services | Library services | As a resident, I want to ask the chatbot how to renew my library books online, so that I can manage my loans and avoid overdue fines. | Medium – Supporting online library renewals helps residents manage loans conveniently and reduces the risk of overdue fines. | 1) Renewal steps explained 2) Library portal linked | Low | Short | Sprint 3
Technical & AI Infrastructure | GPT & RAG integration | As a developer, I want to integrate GPT and retrieval-augmented generation into the chatbot, so that responses are accurate, relevant, and based on council-approved data. | High – Accurate and context-aware responses improve trust in the chatbot and significantly enhance the quality of citizen interactions. | 1) GPT integrated 2) RAG retrieves relevant data | High | Long | Sprint 4
Ethics & Compliance | GDPR & accessibility compliance | As a resident, I want the chatbot to be secure, privacy-aware, and accessible, so that my data is protected and the service is usable by everyone. | High – Ensuring privacy and accessibility protects citizens’ data and guarantees the chatbot can be used safely and inclusively by everyone. | 1) GDPR compliance ensured 2) WCAG 2.1 AA met | High | Medium | Sprint 4