## Status Report
Bradford Council Citizen Conversational AI Agent
Today's date: 15th January 2026
Summary |  |  |  |  | Overall Status (RAG)
We have completed the Project Initiation Phase and are currently in Sprint 1 – Research and Experimentation. During this sprint, each team member is completing their individual research and producing summaries and design maps to support shared understanding and knowledge transfer across the team. In parallel, we are researching suitable data sources for the Bradford Council use case and defining an initial knowledge base structure. This phase also includes early experimentation through the development of an initial Minimum Viable Product (MVP), where a basic conversational agent is created using an LLM API to support simple user interactions. The outcomes of this sprint will inform key design decisions related to system architecture, data and knowledge base structure, and the overall implementation approach as the project transitions into the development phase in the next sprint. |  |  |  |  | Amber
Completed Milestones and Tasks
Description |  | Date | Status | Owner |  | Comments
Project Initiation
Team contract outlining expectations, communication, and teamwork guidelines. |  | 20 Oct 2025 | Completed | Team
Project charter defining goals, scope, deliverables, ethical framework, and timeline |  | 28 Oct 2025 | Completed | Team |  | Provided a clear project direction and aligned team and client expectations.
Objectives and Key Results (OKRs) for technical and organisational progress |  | 11 Nov 2025 | Completed | Team |  | OKRs will be reviewed and refined as the project evolves.
Risk management plan identifying early risks and mitigation strategies |  | 11 Nov 2025 | Completed | Oudat |  | Helped identify technical, ethical, and delivery risks early.
Initial project plan outlining tasks, dependencies, and sprint structure |  | 11 Nov 2025 | Completed | Samik |  | The project plan will be iteratively updated as requirements become clearer.
Communication plan defining communication types, frequency, stakeholders, and methods |  | 11 Nov 2025 | Completed | Uswat |  | This plan would improve coordination and consistency across team and stakeholder interactions.
Product backlog and sprint backlog creation |  | 24 Nov 2025 | Completed | Oudat |  | This would enable structured sprint planning and task prioritisation.
Creation of research mind map |  | 24 Nov 2025 | Completed | Uswat |  | Helped visualise system components and avoid overlap in research areas.
Creation of design mind map |  | 24 Nov 2025 | Completed | Samik |  | This supported early architectural understanding of the AI agent and for the individual reports.
ROAM analysis |  | 15 Dec 2025 | Completed | Samik |  | Clarified risks that could be resolved, owned, accepted, or mitigated.
Project status report |  | 15 Dec 2025 | Completed | Uswat |  | Summarised current progress of the project.
Sprint retrospective |  | 15 Dec 2025 | Completed | Oudat |  | Reflected on initiation phase and identified improvements for next sprint.
Sprint 1 - Research & Experimental Phase
Complete individual research |  | 9 Jan 2026 | Completed | Team |  | Each member focused on assigned research areas aligned to project plan.
Upcoming Milestones and Tasks
Description |  | Date | Status | Owner |  | Comments
Research summaries and design maps for knowledge transfer |  | Jan 2026 | In Progress | Team |  | Aims to consolidate research findings for implementation phase.
Research on suitable data sources and examples |  | Jan 2026 | Upcoming | Uswat |  | Will inform knowledge base and retrieval strategy.
Define initial knowledge base structure |  | Jan 2026 | Upcoming | Oudat |  | Supports scalable and structured data access for the agent.
Create initial conversational agent using LLM API |  | Jan 2026 | Upcoming | Samik |  | First technical prototype to validate interaction flow.
Collate ideas from AI Ethics by Design course |  | Jan 2026 | Upcoming | Team |  | This would inform the design and implementation of the ethical aspect of the project
Develop initial MVP focusing on Bin Collection and Benefits use cases |  | Feb 2026 | Upcoming | Team |  | Initial MVP to validate core conversational flow, knowledge base and implementation.
Top Risks and Issues
Issue |  |  | Impact | Action |  |  | Owner
Inconsistent understanding of project scope across team |  |  | Misaligned research focus and duplicated work | Use research and design mind maps to align understanding |  |  | Team
Difficulty identifying reliable and relevant data sources |  |  | Delays in defining the knowledge base structure | Focus on verified datasets. |  |  | Task Owner
Competing academic workload |  |  | Reduced availability and uneven task progress | Plan tasks weekly and redistribute work where necessary |  |  | Team
Limited experience integrating LLM APIs |  |  | Slower progress on initial agent experimentation | Take courses/ tutorials, start with simple API calls and minimal agent functionality |  |  | Team